## work items
Id | Topic | item | Sub Item | Rally id | Depends On | Estimate (days) | Estimate of non critical(days) | Comments
2 | Project overall | Requirement Document | [5 empty] | root item, we don't really expect it. Full project requirement
3 | Project overall | In-Cloud architecture doc | [5 empty] | architecture document
4 | VPG Management | HLD | HLD |  | 2 | 0 | 10
5 | VPG Management | Create VPG | Create VPG Structure |  | 4 | 5 |  | create objects and identifiers, define structure
6 | VPG Management | Create VPG | Create VPG |  | 8,9 | 15 |  | The full flow to create new VPG, incuding REST API (not including prestitance) and Validations
7 | VPG Management | common management operations | DB Management |  | 5, 90 | 10 |  | Persist and Load VPG Settings in the
8 | VPG Management | common management operations | pontentials on protected side |  | 4 | 10 |  | The full flow to getting "potentials", including the REST API
9 | VPG Management | common management operations | pontentials on recovery side |  | 8 | 20 |  | list of authorized regions (is it automatic?)
10 | VPG Management | Update VPG | update VPG |  | 6, 13 | 10 |  | The full flow to update VPG, incuding REST API (not including prestitance) and Validations
11 | VPG Management | common management operations | Validation "engine" |  | 4 | 10 |  | Framework/infrastrtucute for validating entities (such as VPG)
12 | VPG Management | common management operations | implement validations |  | 6,11 | 10 |  | Validation implementations to be used for Create/Update/Delete VPGs
90 | infra | DB management | Create DB |  |  | 10
13 | VPG Management | VPGs queries | VPG List |  | 6 | 5 |  | Retrieve list of existing VPGs, Also returns the VPGs status
14 | VPG Management | Delete VPG | Delete VPG |  | 13 | 10 |  | Delete VPG from DB, Send message to Replication, Delete all RPGs (incduing snapshots)
15 | VPG Management | REST API |  |  | 5,6 | 10 |  | General infra and Entites conversion
16 | VPG Management | Analytics | google analytics |  | 86, 6 | 10 |  | implementation
17 | VPG Management | FOL - Commit | Change VPG status |  | 9, 37, 85 | 10 |  | Read message from queue and handle it
[6 empty] | Total days: | 10
[6 empty] | sprints: | 0.13333 | assuming 6 concurrent developers

## phase II
Id | Topic | Component | item | Sub Item | Rally id | Depends On | comments | Estimate (days) | Component
|  | analytics | dashboard
|  | Infra | authorizing calls | Access Control ??? |  |  | don't know if it's on the POs backlog. i guess it's not for the first version
|  | Infra | disconnection | from platform in some region
31 | Recovery Operations | common recovery operations | support continuing flows |  |  |  | phase 2? if during an operation we crash we would like to continue the operation (unlike undo in ZVM). the idea is, for example, we'll tag every disk that we converted and then continue from where we failed

## "sprint8" order of work
id | critical paths | US description | sub path | dependent on | Asaf
1 | create vpg | create minimal vpg structure (types classes...) |  |  |  | design and implement recovery data <-- important
2 | create vpg | definition of types
3 | create vpg | create the rest api that accepts it | path1 |  | Ruslan
4 | create vpg | working with the FE | path1 |  |  | implement recoverying of vm based on mocked recovery data
5 | create vpg | potentianls | path1 |  |  | implement recoverying of vm based on recovery data
6 | create vpg | working with DynamoDB and how to work locally work with a DB or mocking it | path 2
7 | create vpg | save/load the vpg to the DB | path 2 |  | Oded
8 | integrate vpg management with replication | work based on the vpg structure (dependent on 1.2) |  |  |  | create initial vpg structure
9 | integrate replication with recovery operations | define recovery data by replication |  |  |  | create rest api that accepts it
10 | integrate replication with recovery operations | replication components writes recovery data | path 1 |  | Ivan
11 | recover vpg | implement recoverying of vm | path 1 |  |  | create initial vpg structure
12 |  | implement recoverying of vpg | path 1 |  |  | save/load vpg structure
13 |  | recover based on recovery data written by replication | path 2
14 | FrontEnd | when can you start develop against ZIC? after infra, facade, mock login for us the most important is create vpg let's start with everything mocked in the wizard vpg and integrate with the BE then we'll start clearing the mocks in the wizard

## PO
Feature
VPG Mgmt
Recovery | Key-Pair
Replication | User Data
Replication | Network Interface
Replication | Volume Encryption - bring your own key
Recovery | Private AMIs
Recovery | Marketplace AMIs
Replication | Volume Properties
Installation
Authentication
Permissions
Google Analytics